DATE:

AGENCY PROPOSED SCHEDULE

CONSTRUCTION MANAGEMENT-AT-RISK (CM-R)

AGENCY:

PROJECT NAME:

PROJECT NUMBER:

|  | Agency Project Manager | Name: Phone: Email: |
| --- | --- | --- |
|  | OSE Project Manager | Name: Phone: Email: |
|  | Agency Program/End-User | Name: Phone: Email: |
|  | Agency receives approval of Alternative Delivery Method from State Engineer | Date: |
|  | Phase I PIP Approval (A-1 approval date) | Date: |
|  | OSE advertises for A/E Services in SCBO | Date: |
|  | Deadline for receipt of proposals for A/E Services | Date: N/A |
|  | Agency conducts short list meeting for A/E interviews | Date: N/A |
|  | Agency conducts interviews for A/E Services | Date: |
|  | Agency requests authority to execute Professional Services Contract | Date: |
|  | OSE approves CM-R Selection Plan | Date: |
|  | Selection Committee assembles CM-R RFQ and advertisement. | Date: |
|  | OSE advertises RFQ in SCBO | Date: |
|  | Agency conducts pre-submittal conference (optional) | Date: N/A |
|  | Deadline for receipt of qualifications per the RFQ | Date: |
|  | Selection Committee assembles RFP package | Date: |
|  | Selection Committee shortlists firms from RFQ package | Date: |
|  | Agency Project Manager sends RFP package to shortlisted firms | Date: |
|  | Pre-proposal Conference for shortlisted firms | Date: N/A |
|  | Deadline for receipt of proposals per the RFP | Date: |
|  | Agency Project Manager evaluates proposals for responsiveness | Date: |
|  | Selection Committee reviews proposals and determines if interviews are necessary | Date: |

|  | If necessary, Selection Committee interviews and ranks prequalified firms | Date: |
| --- | --- | --- |
|  | Agency Head approves Selection Committee’s recommendation | Date: |
|  | Agency completes negotiations and requests concurrence from OSE to post Notice of Intent to Award | Date: |
|  | OSE reviews proposed award package and concurs with the posting of the Notice of intent to Award | Date: |
|  | Agency posts Notice of Intent to Award | Date: |
|  | A/E submits Schematic Design Documents to OSE for review | Date: |
|  | OSE, Agency, A/E and CM-R jointly review Schematic Design Documents | Date: |
|  | OSE sends Schematic Design comments to Agency | Date: N/A |
|  | Phase II PIP Approval (A-1 approval date) | Date: |
|  | Agency and CM-R agree on GMP (Note: GMP may be phased) | Date: |
|  | A/E submits properly completed Construction Documents to OSE for review | Date: |
|  | OSE sends Construction Documents comments to Agency/A/E | Date: |
|  | OSE approves Building/Construction Permit | Date: |
|  | Agency executes Exhibit “A” of the CM-R contract to begin construction | Date: |
|  | CM-R/Contractor begins Construction | Date: |
|  | Agency and A/E schedule Substantial Completion and Certificate of Occupancy/Use Inspections with OSE agreement | Date: |
|  | Agency sends executed Certificate of Substantial Completion to OSE | Date: |
|  | OSE approves Certificate of Occupancy/Use | Date: |
|  | A/E and/or Agency declares Final Completion | Date: |
|  | Agency sends executed Certificate of Final Completion to OSE | Date: |